# Makkah Royal Clock Tower

AI-Powered Clock Tower Management System

Development Proposal Document

Dated: 07/04/2026

SOFTWARE

# Introduction

Argon Teq proposes the design and development of a comprehensive, AI-driven management ecosystem for the Makkah Royal Clock Tower. The primary objective is to deliver an operationally precise, secure, and scalable platform that integrates real-time IoT monitoring, structural health analytics, crowd and security management, predictive maintenance, digital twin simulation, and commercial intelligence — all accessible via a modern web dashboard and mobile AR application.

This engagement extends beyond a conventional software delivery. It is envisioned as a business-critical, mission-grade digital platform that serves the operational, safety, heritage, and commercial imperatives of one of the world's most iconic landmarks.

# Objectives

The primary objectives of this project are aligned with both operational excellence and the long-term preservation and commercial performance of the Clock Tower:

  - Achieve clock-mechanism precision tracking with AI-predicted drift correction and automated maintenance scheduling

  - Deliver real-time structural health monitoring with anomaly detection at ≥95% accuracy and emergency repair reduction of ≥40%

  - Provide live environmental and security surveillance with crowd density management and sub-2-second alert processing

  - Deploy a fully operational 3D digital twin with scenario simulation capability for storms, mechanical failure, and crowd surges

  - Enable predictive maintenance with AR-assisted technician guidance via iOS and Android mobile applications

  - Automate commercial and contract intelligence including lease renewals, tenant compliance, and revenue optimization

  - Build a scalable, secure cloud architecture meeting 99.9% uptime and ≤2s latency requirements

# Scope of Work

The scope of work is organized across four deployment phases, each representing a critical layer of the overall AI-powered ecosystem.

Phase 1 — Sensor & Edge Device Installation (Weeks 1–6) (To be Done by IoT team)

Procurement, installation, and calibration of all IoT hardware across the tower structure, including:

- Clock mechanism sensors: rotary encoders, vibration sensors, motor current sensors

- Structural sensors: accelerometers, tilt sensors, strain gauges, vibration sensors at tower corners and beams

- Environmental sensors: temperature, humidity, air quality (PM2.5/PM10), wind speed, precipitation

- Security & crowd sensors: HD IP cameras with AI motion detection, infrared/night vision, door/window contact sensors, crowd density sensors

- Commercial sensors: occupancy sensors, visitor flow analytics, POS integration hardware

- Edge AI modules: local preprocessing, anomaly detection, MQTT/HTTPS cloud communication, alert buffering

Phase 2 — Cloud Platform & Dashboards (Weeks 5–12)

Core cloud infrastructure, databases, RESTful APIs, web dashboard, mobile application, and notification delivery engine. Key deliverables include Terraform/Pulumi infrastructure, InfluxDB and PostgreSQL databases, FastAPI endpoints, React/TypeScript dashboard with live WebSocket panels, React Native/Flutter mobile app, and Firebase/SendGrid/Twilio notification engine.

Phase 3 — AI Models & Digital Twin (Weeks 9–20)

Full AI/ML capability stack including LSTM structural prediction, Random Forest clock drift correction, CNN crowd and commercial analytics, Three.js real-time 3D digital twin with scenario simulation, AR-assisted maintenance workflows (ARKit/ARCore), predictive maintenance scheduler, and commercial system integrations (POS, lease management).

Phase 4 — Optimization & Commercial Intelligence (Weeks 14–27)

Reinforcement learning for visitor flow optimization, revenue and lease automation engines, energy optimization module, MLOps pipelines (Evidently/Airflow), full E2E QA, security penetration testing, API documentation (OpenAPI 3.0), and complete knowledge transfer and handover.

# Development Timeline

The following tables detail all sub-tasks across Phases 2, 3, and 4, with frontend and backend day estimates and individual cost at $30 USD/hour. Phase 1 hardware installation tasks are managed separately by the IoT/infrastructure team.

Phase 2 — Cloud Platform & Dashboards (Weeks 5–12)

| Task ID | Description | Category | FE (Days) | BE (Days) | Cost (USD |
| --- | --- | --- | --- | --- | --- |
| P2-01 | Terraform/Pulumi: VPC, EKS, RDS PostgreSQL, Redis, S3, API GW | DevOps | — | 3 | $720 |
| P2-02 | InfluxDB Cloud cluster + retention policies (1yr hot / 5yr cold) | DevOps | — | 2 | $480 |
| P2-03 | Kafka/Kinesis stream pipeline: MQTT → ingest → InfluxDB | Backend | — | 3 | $720 |
| P2-04 | PostgreSQL schema: users, roles, alerts, maintenance, contracts, twin | Backend | — | 5 | $1,200 |
| P2-05 | FastAPI — /sensors/data endpoint (GET, streaming, pagination) | Backend | — | 3 | $720 |
| P2-06 | FastAPI — /alerts endpoints (CRUD, acknowledge, escalate) | Backend | — | 3 | $720 |
| P2-07 | FastAPI — /maintenance endpoints (schedule, assign, complete) | Backend | — | 3 | $720 |
| P2-08 | FastAPI — /visitors and /contracts placeholder endpoints | Backend | — | 3 | $720 |
| P2-09 | OAuth2 + JWT auth service + RBAC middleware (5 roles) | Security | — | 3 | $720 |
| P2-10 | React + TypeScript dashboard scaffold + routing + RTL support | Frontend | 3 | — | $720 |
| P2-11 | Dashboard — Clock & Structural KPI panels (live WebSocket) | Frontend | 3.5 | — | $840 |
| P2-12 | Dashboard — Environmental & Security panels | Frontend | 3 | — | $720 |
| P2-13 | Dashboard — Alerts feed & maintenance task list | Frontend | 2 | — | $480 |
| P2-14 | Dashboard — Historical trend charts (Recharts / Grafana embed) | Frontend | 3 | — | $720 |
| P2-15 | Notification engine — Firebase FCM push integration | Backend | — | 3.5 | $840 |
| P2-16 | Notification engine — SendGrid email + Twilio SMS + escalation | Backend | — | 3 | $720 |
| P2-17 | React Native / Flutter app scaffold + auth + dashboard views | Mobile | 4 | — | $960 |
| P2-18 | Mobile — push notification integration + alert deep-link | Mobile | 2 | — | $480 |
| P2-19 | CI/CD pipeline — GitHub Actions: test, build, deploy to EKS | DevOps | — | 2 | $480 |

| Task ID | Description | Category | FE (Days) | BE (Days) | Cost (USD |  |
| --- | --- | --- | --- | --- | --- | --- |
| P2-20 | Phase 2 integration + load test (99.9% uptime, ≤2s latency) | QA | — | 3 | $720 |  |
|  | Phase Subtotal — Cloud Platform & Dashboards |  | 666 hrs |  | $19,980 |  |

Phase 3 — AI Models & Digital Twin (Weeks 9–20)

| Task ID | Description | Category | FE (Days) | BE (Days) | Cost (USD |
| --- | --- | --- | --- | --- | --- |
| P3-01 | LSTM data prep: feature engineering from vibration sequences | ML | — | 2 | $480 |
| P3-02 | LSTM model training — structural vibration trend prediction | ML | — | 4 | $960 |
| P3-03 | LSTM inference endpoint — containerized (FastAPI + Docker) | ML | — | 2 | $480 |
| P3-04 | LSTM retraining Airflow DAG (weekly; drift-triggered) | ML | — | 2 | $480 |
| P3-05 | Random Forest clock drift — retrain on live data, calibrate | ML | — | 2.5 | $600 |
| P3-06 | Random Forest — edge deployment (ONNX serialized to Jetson) | ML | — | 1.5 | $360 |
| P3-07 | CNN data pipeline from CCTV feeds (NVIDIA DeepStream) | ML | — | 3 | $720 |
| P3-08 | CNN training — crowd density estimation (people per m²) | ML | — | 3 | $720 |
| P3-09 | CNN training — commercial zone occupancy classification | ML | — | 2 | $480 |
| P3-10 | CNN inference deployment + dashboard camera overlay | ML | 2 | 2 | $960 |
| P3-11 | BIM / 3D model acquisition & validation (client deliverable) | Digital Twin | — | 2 | $480 |
| P3-12 | Three.js web viewer — load & render BIM tower model (LOD2) | Digital Twin | 5 | — | $1,200 |
| P3-13 | Sensor ID → 3D position mapping (JSON sensor-to-model map) | Digital Twin | 2 | 2.5 | $1,080 |
| P3-14 | Real-time sensor overlay on 3D model (colour heatmaps) | Digital Twin | 3 | — | $720 |
| P3-15 | Scenario simulation: storm, high wind, mech. failure, crowd surge | Digital Twin | 5 | 5 | $2,400 |
| P3-16 | Digital twin UI — control panel + simulation timeline scrubber | Digital Twin | 3.5 | — | $840 |
| P3-17 | AR mobile — ARKit (iOS) + ARCore (Android) SDK setup | Mobile/AR | 2 | — | $480 |
| P3-18 | AR mobile — 3D component overlay anchoring (maintenance) | Mobile/AR | 3.5 | — | $840 |
| P3-19 | AR mobile — repair instruction step-by-step overlay UI | Mobile/AR | 2 | — | $480 |
| P3-20 | Predictive maintenance scheduler (rule + ML hybrid engine) | Backend | — | 7.5 | $1,800 |
| P3-21 | Maintenance task assignment + technician push notification | Backend | — | 3 | $720 |
| P3-22 | POS system integration — data ingestion API | Commerci al | — | 3 | $720 |

| Task ID | Description | Category | FE (Days) | BE (Days) | Cost (USD |  |
| --- | --- | --- | --- | --- | --- | --- |
| P3-23 | Lease management system integration + data normalization | Commerci al | — | 3 | $720 |  |
| P3-24 | Commercial dashboard — occupancy, revenue, compliance KPIs | Frontend | 2.5 | — | $600 |  |
|  | Phase Subtotal — AI Models & Digital Twin |  | 633 hrs |  | $18,990 |  |

Phase 4 — Optimization & Commercial Intelligence (Weeks 14–27)

| Task ID | Description | Category | FE (Days) | BE (Days) | Cost (USD |
| --- | --- | --- | --- | --- | --- |
| P4-01 | RL environment setup — visitor flow sim from floor plan data | ML | — | 2.5 | $600 |
| P4-02 | RL agent training — queue routing & crowd management policy | ML | — | 3.5 | $840 |
| P4-03 | RL inference deployment + evacuation guidance integration | ML | — | 1.5 | $360 |
| P4-04 | Revenue optimization AI — occupancy benchmarking alerts | Backend | — | 5 | $1,200 |
| P4-05 | Lease renewal & SLA breach alert automation engine | Backend | — | 7.5 | $1,800 |
| P4-06 | Energy optimization module — cross-correlate env + occupancy | Backend | — | 4 | $960 |
| P4-07 | Energy recommendations dashboard panel | Frontend | 2.5 | — | $600 |
| P4-08 | Evidently / Alibi drift monitoring for all production models | ML/Ops | — | 2 | $480 |
| P4-09 | Airflow/Prefect DAGs — automated weekly retraining all models | ML/Ops | — | 3 | $720 |
| P4-10 | Full system E2E integration test (all modules, all roles) | QA | — | 3 | $720 |
| P4-11 | Security penetration test (RBAC, API, sensor data integrity) | Security | — | 4 | $960 |
| P4-12 | Performance validation: uptime 99.9%, latency ≤2s, alerts ≤2s | QA | — | 1.5 | $360 |
| P4-13 | API documentation — OpenAPI 3.0 spec + Postman collection | Docs | — | 5 | $1,200 |
| P4-14 | System runbooks — operations, incident response, maintenance | Docs | — | 1.5 | $360 |
| P4-15 | User training — Admin, Technician, Commercial Manager roles | Training | — | 1 | $240 |
| P4-16 | Knowledge transfer & handover to operations team | Handover | — | 1 | $240 |
|  | Phase Subtotal — Optimization & Commercial Intelligence |  | 450 hrs |  | $13,500 |

SOFTWARE COST SUMMARY PHASE WISE

| Phase | Timeline | Total Hours | Cost (USD) |
| --- | --- | --- | --- |
| Phase 2 — Cloud Platform & Dashboards | Weeks 5–12 | 666 | $19,980 |
| Phase 3 — AI Models & Digital Twin | Weeks 9–20 | 633 | $18,990 |
| Phase 4 — Optimization & Commercial Intelligence | Weeks 14–27 | 450 | $13,500 |
| GRAND TOTAL — ALL PHASES | 18–27 Weeks | 2187 | $65,610 |

HARDWARE

While the software layer provides the intelligence, the hardware and firmware layer provides the ground truth. This proposal covers the end-to-end development of the physical sensing layer, custom PCBA (Printed Circuit Board Assembly) design for edge processing, and the embedded firmware architecture necessary to meet the $99.9\%$ uptime and $\pm0.1$ sec precision requirements.

### 2. Objectives & Engineering Standards

- Precision Acquisition: High-fidelity data capture for clock drift correction ($\pm0.1$ sec).

- Structural Integrity: Anomaly detection with $\ge95\%$ accuracy through high-frequency sampling.

- Embedded Resilience: Firmware-level "Local Alert Buffering" to prevent data loss during network outages.

- Industrial Compliance: Hardware designed for high-altitude environmental stress (wind, heat, vibration).

### 3. Technical Architecture & Engineering Scope

#### A. PCBA Design & Sensor Clusters

Our hardware engineers will design custom Sensor Interface PCBAs to normalize signals from disparate industrial sensors into a unified Edge Gateway.

- Clock Mechanism Schema: Integration of rotary encoders, $\pm0.01$ g vibration sensors, and 1 Hz motor current sensors.

- Structural Schema: Deployment of $\pm16$ g accelerometers and $\pm0.01^{\circ}$ tilt sensors across tower corners and central columns.

- Environmental/Security Schema: Integration of PM2.5/PM10 laser sensors, ultrasonic anemometers, and HD AI-vision modules.

#### B. Firmware Architecture

The firmware engineers will develop a multi-threaded RTOS (Real-Time Operating System) environment for the Edge AI modules.

- Edge Preprocessing: Local execution of Random Forest and LSTM algorithms for immediate anomaly detection.

- Communication Stack: Robust MQTT/HTTPS stack with TLS 1.3 encryption.

- Reliability Layer: A firmware-level watchdog and local storage buffer (InfluxDB Edge) to ensure 0% data loss during 15-minute escalation windows.

### 4. Deployment & Testing Roadmap (Weeks 1–10)

| Phase | Task Description | Team |
| --- | --- | --- |
| P1-01 | System Architecture & Schema Design: Finalizing wiring diagrams, sensor-to-model mapping, and communication protocols. | HW/FW Lead |
| P1-02 | PCBA Design & Prototyping: Custom PCB layout for signal conditioning and Edge AI housing. | HW Engineers |
| P1-03 | Firmware Development: Coding the RTOS, MQTT drivers, and local AI inference engines. | FW Engineers |
| P1-04 | Hardware-in-the-Loop (HiL) Testing: Stress-testing sensors against simulated "Storm/High Wind" scenarios. | QA/FW |
| P1-05 | On-Site Deployment: Physical mounting of sensors at exact tower positions (Corners, Shafts, Beams). | Field Techs |
| P1-06 | Calibration & Handshake: Phase 1 finalization with cloud-to-edge connectivity validation. | HW/FW Engineers |

### Detailed Costing (Hardware Phase)

| ID | Task | Hours | Cost (USD) |
| --- | --- | --- | --- |
| HW-ENG | Architecture, Schema Design, and PCBA Layout | 120 |  |
| FW-ENG | Firmware Development (Edge AI, MQTT, Buffer Logic) | 160 |  |
| HW-INST | On-site Sensor Installation & Wiring (Structural/Clock) | 200 |  |
| HW-TEST | System Validation & Performance Stress Testing | 60 |  |
|  | Engineering & Installation Total | 540 hrs | 28,800 |
|  | Estimated Bill of Materials (Sensors, PCBAs, Gateways) |  | 19,900 |
|  | TOTAL COST OF HARDWARE |  | 48,700 |